## Manual Chart
GANTT CHART TEMPLATE
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
First Sample Project
| Research PyGame | 2019-02-19 | 2019-02-21 | 3 | All | 100%
| Expand on exisiting OOP model | 2019-02-19 | 2019-02-26 |  | Kevin and Somali | 80% | bar: WEEK 2 M to WEEK 2 T
| Create Card Images | 2019-02-19 | 2019-03-12 | 16 | Somali | 60% | bar: WEEK 1 F to WEEK 2 Th
| Gather Music Files | 2019-02-26 | 2019-03-07 | 8 | Nicole and Kevin | 40% | bar: WEEK 2 T to WEEK 3 M
| Create Cards/CardDeck classes | 2019-02-26 | 2019-03-01 | 4 | Kevin | 20% | bar: WEEK 2 Th to WEEK 3 W
| Create menu framework | 2019-02-27 | 2019-03-01 | 3 | Kevin | 10% | bar: WEEK 3 T to WEEK 3 Th
| Test first iteration | 2019-03-01 | 2019-03-03 | 1 | Ibrahim | bar: WEEK 3 T to WEEK 3 Th
Second Sample Project
| Add multiplayer functionality | 2019-03-02 | 2019-03-06 | 3 | Nicole | 100%
| Upgrade ui graphics | 2019-03-05 | 2019-03-28 | 18 | All | 80%
| Adjust exisiting classes | 2018-02-11 | 2018-02-16 | 5 | All | 60%
| Test second iteration | 2019-03-28 | 2019-03-30 | 2 | Ibrahim | 40%
Third Sample Project
100%
80%
60%
40%
20%
10%
Fourth Sample Project
100%
80%
60%
40%
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])