## Manual Chart
GANTT CHART TEMPLATE
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
First Iteration
| Research PyGame | 2019-02-19 | 2019-02-21 | 3 | All | 100% | bar: WEEK 1 T to WEEK 1 Th
| Expand on exisiting OOP model | 2019-02-19 | 2019-02-26 |  | Kevin and Somali | 70% | bar: WEEK 1 T to WEEK 1 Th
| Create Card Images | 2019-02-19 | 2019-03-12 | 16 | Somali | 20% | bar: WEEK 1 T to WEEK 1 Th
| Gather Music Files | 2019-02-26 | 2019-03-07 | 8 | Nicole and Kevin | 0%
| Create Cards/CardDeck classes | 2019-02-26 | 2019-03-01 | 4 | Kevin | 50%
| Create menu framework | 2019-02-27 | 2019-03-01 | 3 | Kevin | 50%
| Test first iteration | 2019-03-01 | 2019-03-03 | 1 | Ibrahim | 0%
Second Iteration
| Add multiplayer functionality | 2019-03-02 | 2019-03-06 | 3 | Nicole | 0%
| Create buttons | 2019-03-02 | 2019-03-05 | 2 | Irbahim | 0%
| Upgrade ui graphics | 2019-03-05 | 2019-03-28 | 18 | All | 0%
| Adjust exisiting classes | 2019-03-05 | 2019-03-28 | 18 | All | 0%
| Test second iteration | 2019-03-07 | 2019-03-10 | 2 | Ibrahim | 0%
Third Iteration
| Add code to documents stats | 2019-03-07 | 2019-03-12 |  | Somali | 0%
| Add display functions for stats | 2019-03-07 | 2019-03-12 |  | Kevin | 0%
| Add highscore database | 2019-03-07 | 2019-03-12 |  | Ibrahim | 0%
| Start writing presentation slides | 2019-03-14 | 2019-03-21 |  | Nicole | 0%
| Debug program | 2019-03-21 | 2019-03-28 |  | All | 0%
| Test third iteration | 2019-03-28 | 2019-03-30 |  | Nicole | 0%
Fourth Iteration
| Final iteration test | 2019-04-02 | 2019-04-05 |  | All | 0%
| Proof read presentation slides | 2019-04-05 | 2019-04-17 |  | Nicole | 0%
| Project Presentation Practice | 2019-04-08 | 2019-04-12 |  | All | 0%
| Project Video | 2019-04-12 | 2019-04-14 |  | All | 0%
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])